MISCADA: Professional Skills - Software Development Assignment

We are tasked with outlining the planning (development) process of a small local conference occurring on 1st May 2022. The choice of a development approach is contingent on 3 factors:

- Project variables (stakeholders, time, cost)

- Organisation (Structure, culture, policies, size)

- Outcome (Product, service, result)

  - Innovation

  - Clarity

  - Scope

  - Risk

  - Safety

  - Regulations

We examine the factors in turn in the table below, examining the compatibility of each with a predictive and adaptive approach, ranking each from 1 to 5 (predictive to adaptive).

| Factors | Context | Predictive/Adaptive | Rating |
| --- | --- | --- | --- |
| Project variables (stakeholders, time, cost) | The project stakeholders are the conference attendees and the organisers. There is over 6 months between the start of the planning process and the date of the conference The human resource for organising and running the conference is known, the financial resource is dependent on the number of tickets sold. | Broadly these factors suggest a predictive approach. The stakeholders’ requirements are unlikely to change, e.g. the topic and nature of activities at the conference are fixed well in advance, and we can confidently predict these ahead of time. The length of time until the conference suggests that there is little time for the iterations required in an adaptive approach. The financial resource is reliant on the number of tickets sold. The finances can either be continually updated with attendance data, or once an initial level of interest is known finances for different attendance scenarios can be planned. Therefore, the finance issue can be approached predictively or adaptively. | 2 |
| Organisation (Structure, culture, policies, size) | We assume the organisation is relatively new, running the inaugural version of the conference. | An organisation organising a small local conference is itself likely to be small. As it is also new, with little structure, policies and culture to speak of, it would heavily suggest an adaptive approach. | 5 |
| Outcome (Product, service, result) | The desired outcome is delivery of a conference which sufficiently meets the stakeholders’ requirements | See below | See below |
| Innovation | Conferences are routinely run. | There is little innovation, the project should be relatively simple – suggesting a predictive approach. | 1 |
| Clarity of requirements | Consultation with the stakeholders at the start of the planning process can ensure their requirements are made clear. | Accurately capturing the scope and requirements early, and have them not be subject to change, would allow for a predictive approach. The stakeholders for this conference as particularly busy and as such they are unable to contribute often to the planning as an adaptive development process would require. | 1 |
| Stability of scope | The scope should be relatively stable as the scoping process is relatively easy and should not be particularly reactive to the development of the conference plan. |  |  |
| Risk | There exists a financial, safety and reputational risk to the stakeholders. | The risks are well defined and predictable, this would suggest using a predictive approach. | 1 |
| Safety | The requirements for holding a safe conference are defined by statute. Conference venues will be aware of these. | The safety requirements are well defined and easy for the organising committee to become aware of via colleagues at the chosen conference venue. This would suggest using a predictive approach. | 1 |
| Regulations | Other than safety regulations there are no other relevant regulations. | This does not suggest either approach. | 3 |
|  |  | Total Score | 16 |

From the score analysis in the table, we conclude that the project should be planned using a predictive approach. Scores can be anywhere in the range of 9 (predictive) to 36 (adaptive). 17 is a low score suggesting a predictive approach be employed.

We shall employ the waterfall method with task dependencies set such that: the financial risk is reduced by examining multiple income (attendance) scenarios, and the project is clearly scoped in advance. By carrying these two tasks out early on, we can remove much of the adaptive elements of the project and hence the waterfall method (a predictive approach) will be appropriate.